10/66 Dementia Research Group

Population-based study

POPULATION-BASED STUDY – LIFE2YEARS

MANUAL VERSION 1.2

October 2015

CONTENTS

BACKGROUND/ OVERVIEW								4

1.1 Objectives

1.2 Sampling

1.3 Assessments

1.4 Operationalisation – key elements of LIFE2YEARS1066 methodology

1.5 Estimated timelines for fieldwork

2. Resources required for the study					7

2.1 The principal investigator

2.2 Study coordinator

2.3 Door-knockers

2.4 Interviewers

2.5 Local collaborators

2.6 Equipment/ materials

3. KEY STAGES IN THE PROCESS							9

3.1 Sensitizing the local community

3.2 Door-knocking (new prevalence wave)

3.3 Tracing and recontacting remaining baseline participants,

not resident in the catchment area (final incidence wave)

3.4 The prevalence and incidence wave surveys

3.5 Blood sample collection

3.6 18 month nested cohort study

4. THE ASSESSMENTS									21

4.1 Overall structure

4.2 Overview of the structure of the LIFE2YEARS assessments – Set A

4.3 Overview of the structure of the LIFE2YEARS assessments – Set B

4.4 Overview of the structure of the LIFE2YEARS assessments – Set C

4.5 Translation of assessments

4.6 Further information on assessments

5. FEEDBACK TO PARTICIPANTS							26

6. RESEARCH WORKER TRAINING							27

6.1 Training of doorknockers

6.2 Training for interviewers

7. planning for blood sample collection					28

8. ETHICAL ASPECTS									29

8.1 Ethics review

8.2 Training interviewers in approaching potential participants, and seeking and obtaining informed consent

9. PILOT STUDIES										31

10. READY TO GO!										31

11. IMPLEMENTATION OF THE SURVEY PROTOCOL				31

APPENDICES										32

The purpose of this manual is to provide an overview of the objectives, methodology and operational procedures for the 10/66 LIFE2YEARS project. The main users are intended to be the Principal Investigators and Study Coordinators in each country. We have also prepared separate manuals for the study coordinator, interviewers, data managers, door-knockers and phlebotomists, which provide more information on the roles and responsibilities of those individuals, and the operational procedures that they should follow.

1. BACKGROUND/ OVERVEW

1.1 Objectives

The main protocol objectives of the LIFE2YEARS1066 study are

1. To conduct a new prevalence wave survey in the catchment area sites used for the previous baseline and incidence waves

2. To complete a final incidence wave of those previously interviewed in the original baseline

3. To conduct a nested cohort study of n=300 per site identified as ‘high risk’ or ‘low risk’ of experiencing the onset of needs for care.

LIFE2YEARS data collection will be carried out around 8-12 years after the baseline interview and 6-7 years after follow-up data collection.

1.2 Sampling

For the LIFE2YEARS study, the ‘new prevalence wave survey’ will include all those currently normally resident in the catchment area who will be aged >=65 years on the new census date. They will comprise

a) previous participants in 10/66 baseline surveys, who survive and remain resident in the area

b) those long-term residents of the area who have aged to 65 years in the interval since the baseline survey

c) those aged >=65 years who have migrated into the catchment area since the baseline survey

In addition, for the purposes of the ‘final incidence wave’, we want to resurvey ALL remaining survivors of the original baseline survey, regardless of their current area of residence. They will comprise all participants who completed valid interviews in the baseline survey regardless of their status (interviewed/ refused/ not traced/ uncontactable) at the follow-up phase

Evidently, there will be much overlap between the participants in the ‘new prevalence wave’ and the ‘final incidence wave’. The ‘new prevalence wave’ will exclude those participants in the ‘final incidence wave’ who have moved out of the study catchment area. The ‘final incidence wave’ will exclude participants in the ‘new prevalence’ wave who were not included in the original baseline survey (i.e. inmigrants and those who have aged to >=65 years since baseline). The relationship and overlap between the ‘new prevalence wave sample’ and the ‘final incidence wave sample’ is summarised schematically in Figure1 below.

Figure 1.1

Schematic diagram of relationship between ‘new prevalence wave sample’ and ‘final incidence wave sample’

1. 3 Assessments

All participants will receive exactly the same full LIFE2YEARS assessment, regardless of whether they form part of the ‘new prevalence wave’, the ‘final incidence wave’ or both. The only two exceptions are that

a) only the prevalence wave sample will be invited to give fasting blood samples

b) only the final incidence wave sample will receive a key informant interview after the death of a participant -

- a verbal autopsy interview to establish date and cause of death and

- an adapted informant interview (‘informant (deceased)’) to establish if there was an onset of probable dementia before death

For 300 prevalence wave participants in each site (the nested cohort), we will be collecting additional follow-up data (a brief older person’s interview, cognitive interview, and abbreviated versions of the informant interviews and the NEUROEX) 18 months after their initial LIFE2YEARS interview.

1.4 Operationalisation - key elements of LIFE2YEARS1066 methodology

1.4.1 Door-knocking will need to be completed, in its entirety, and quickly, BEFORE interviewing begins. We will modify (in effect merge) some of the methods used in the baseline and incidence waves of the population-based studies. The door-knocking process will include both

a) systematic mapping and enumeration of ALL households in the catchment area (as carried out in the baseline survey) AND

b) simultaneous tracing of surviving participants of the original baseline survey, and linkage to their original IDs

1.4.2 Interviewing should also be carried out as quickly as possible, to ensure that the 18 month follow-up can be completed well within the period of grant funding. Ideally interviewing should be completed within one year, with the final follow-up interviews then to be completed two and a half years after the start of the interviewing process.

1.4.3 Data entry should be completed within two weeks of data collection, and copies of the data entry files regularly transmitted to the London Centre for processing and selection of suitable cohort participants. Blood samples will be processed locally, and then, subject to approvals in your country, transferred to UK for biochemistry assays, and genotyping

1.5 Estimated timelines for fieldwork

| Month | Door- Knocking | Prevalence wave interviews | Tracing and linking | Final incidence wave IVs + verbal autopsies | Nested cohort selection | Nested cohort IVs |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | M1-2 (2 months) |  | M1-20 (20 months) |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  | M3-14 (12 months) |  | M3-20 (18 months) |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |
| 15 |  |  |  |  | M15-20 (6 months) |  |
| 16 |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |
| 21 |  |  |  |  |  | M21-32 (12 months) |
| 22 |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |

2. RESOURCES REQUIRED FOR THE STUDY

2.1 The principal investigator

The principal investigator takes overall scientific and ethical responsibility for the study locally, as well as liaising with the study co-ordinator to ensure quality control in every aspect of the study, and to try to ensure that the study is completed in a timely fashion.

2.2 Study coordinator

The study co-ordinator (SC) should have relevant background and skills in research. They will report directly to the principal investigator (PI) in each centre, and will be responsible for the day to day conduct of the research; in particular a) training, b) quality control and c) data management

One full-time fully funded study co-ordinator is required in addition to the interviewer resource. While the co-ordinator could (and should) carry out some field interviews so that they understand the work of the interviewers, and can appreciate better and deal with problems arising in the field work, they should have most of their time free to coordinate and supervise the project. They should be employed full-time.

2.3  Door-knockers

A door-knocking team should be assembled to carry out the task of re-mapping and re-doorknocking the catchment area. To complete this task within a one month period a team of 10-12 motivated, trained and supervised individuals may be required. These staff need not be high-level (completed secondary education should suffice), but they should be able to follow a simple protocol accurately and diligently, and approach the public in a professional manner at all times. The use of volunteers may be considered, where available and approrpiate.

2.4  Interviewers

Interviewers should be graduates, but do not need to be health care workers (for example social science graduates would be appropriate). The main qualifications are intelligence, willingness and diligence. All other skills can be provided by careful training (see below). Suitably qualified interviewers who are also residents of the catchment area may be particularly useful for their local knowledge and acceptability to participants. Some centres will want to make other arrangements (for example, using public health doctors as interviewers). This is fine. However, those with less than graduate level education (eg basic level health workers) should not be used, as the data quality is likely to suffer.

For an estimated sample size of 2000 (new prevalence wave) we have estimated that five to six full-time interviewers would be required. This is based on an estimate of an average of 1.5 interviews to be completed each working day, and 20 working days per interviewer per month. Each interviewer would therefore complete 30 interviews per month. For 5.5 interviewers this would mean 150 interviews completed per month, meaning that the whole survey would be completed in 12 months (M3-14). Fewer interviewers will be required during the tracing and interviewing of the remainder of baseline participants no longer resident in the catchment area (final incidence wave, M15-20). The 18 month follow-up of 300 nested cohort participants can be completed by 1-2 interviewers (25 interviewers per month).

2.5 Local Collaborations

You should recruit a local steering committee for the 10/66 project, consisting of multidisciplinary scientific and technical experts Depending upon the background of the principal investigator, it will be important to identify individuals with the following additional expertise to be members of the study team and to advise on the implementation of the study protocol. These might usefully be recruited as a study steering committee, meeting regularly during the preparation period and field research period. They could of course then collaborate with the local analysis of data and preparation of papers reporting local findings.

An epidemiologist

A biostatistician

A psychiatrist

A gerontologist

A haematologist

A biochemist

A geneticist

2.6 Equipment/ Materials

2.6.1 Paper questionnaires

Each interviewer will require a well laid out copy of each interview translated into the local language. Responses to each question could be coded on these sheets, but if you decide to do this you will need to pay for the photocopying or printing costs for 2000 copies of each complete assessment, which may be expensive. An alternative is for each interviewer to have a single copy of the full assessment, and then to code responses on to a data entry form. Data entry forms for all questionnaires are available on the 10/66 intranet site.

2.6.2 Equipment for the physical examination

Each interviewer will require

A tape measure (made out of cloth or paper, 2 metres long if possible)

A digital sphygmomanometer

A digital hand grip strength measuring device

A digital spirometer

A piece of string exactly five metres long

A set of weighing scales

A book or similar to place on the head of the participant when measuring height

A stopwatch or a watch with a second hand

2.6.3 Equipment for phlebotomy

For those centres taking blood samples, you will require for each participant

Swabs

*A needle

* A 20 ml syringe

* (a butterfly and two 10ml syringes might be a good alternative)

One 5-10ml plastic EDTA sample bottle (for haematology and DNA)

One 5ml plain clot bottle (for biochemistry)

One 2.5ml fluoride oxalate bottle (for glucose)

2.6.4 Computing facilities

One desktop or lap top computer, per site, will be dedicated to data entry, so that the data manager has access to it at all times and can enter data as it is collected . Data entry files will be provided for each component of the LIFE2YEARS study. These should be located in a c:\ data directory on the hard drive.

3. KEY STAGES IN THE PROCESS

3.1 Sensitizing the local community

Most sites have now completed several editions of the local 10/66 study newsletter. A new newsletter will be a good way to inform the community of the upcoming LIFE2YEARS study. This can also be used to keep participants in the previous surveys and their families up to date with the progress of the study and its outcomes, and so that they appreciate the value of their contribution. A newsletter can also be used to introduce 10/66 and LIFE2YEARS to new participants. Make sure that you thank previous participants on the newsletter! Include any local/ international information that you feel would reinforce to the participants the importance of the work e.g. newspaper articles, findings from the survey etc. Consider also holding one or more stakeholder workshops in the run in to the study, involving community leaders etc as well as participants. If people have heard little from the study recently, they may not be inclined to participate.

3.2 Door-knocking (new prevalence wave)

3.2.1 General procedures

For the original baseline wave of the survey, most sites carried out a ‘rolling door- knock’, This comprised first door-knocking a small area, then immediately moving on to completing the interviews - then moving on to the next area and repeating the process, and so on. This will not work so effectively for the new study, in which we are hoping, simultaneously to trace survivors of the original baseline, and link them to their original baseline and incidence data records. Therefore, we propose that the door-knocking is completed in its entirety, by a large team, before interviewing commences.

It may be helpful to map the households in the catchment area before starting door-knocking. This task, which can be started before ethical approval, involves identifying every household and determining its address. The catchment area may well have changed since baseline with some buildings demolished and others new ones constructed.

After ethical approval has been received, the door-knocking team will then enumerate the catchment area by visiting, systematically all of the households. They will also carry with them a register of the last known addresses of all those who were participants in the baseline survey and are not known to be deceased. The register, provided by the London Centre will include the following identifiers,:

HOUSEID

PARTICID

DOI 								(date of interview)

NAME

ADDRESS

NAMES AND ADDRESSES OF THREE CONTACTS 	(to facilitate follow-up of those

who had moved away)

AGE

GENDER

EDUCATION LEVEL

MARITAL STATUS

STATUS AT FOLLOW-UP 	(interviewed, refused, uncontactable, not traced)

You should follow these general door-knocking procedures

- Door-knocking can be completed quite quickly and cheaply, using large numbers of, for example, students/ volunteers etc. However, remember that the door-knocking task will require training, and supervision, and spot checks should be carried out to ensure that it is done well.

- Door-knockers should carry study ID, and be dressed appropriately

- The door-knockers will attempt to speak to somebody in every household. Therefore if there is no reply, they should return again later, and not rely upon information from neighbours, other than as a last resort, after three attempts at gaining access to the household, at different times and days of the week have failed. It may be useful to carry out some of these visits in the evening and at weekends.

- The census date will be the date on which you plan to start your survey work. Thus if you are door-knocking in April, and your census date is 1st June, you will record the name of an older person who is 64 but will be 65 in May. That person will be eligible for inclusion in the survey.

- If in any doubt about the age of an older person, and whether or not they will be 65 years or over on the census date, the door-knocker should be instructed to record the name of the older person anyway. The age will be clarified by the survey interviewers, when they apply the age ascertainment procedures in the household interview (see below). Those who turn out not to be eligible can be excluded at that stage.

- Note that for any nursing homes or residential care homes that you find in the catchment area, you should INCLUDE those residents whose normal address before moving into the home was in the catchment area, but EXCLUDE those who had lived outside of the catchment area, and moved into the catchment area for the specific purpose of being cared for in the care home

3.2.2 What information is to be collected?

The door-knockers will record

a) the address of each household, each of which will be allotted a LIFE2YEARS household ID (HOUSENO)

b) the number of residents, stratified by age group, who are normally resident in the household

c) the names of all those considered to be aged 65 or over on the census date, each of whom will be allotted a LIFE2YEARS participant ID (PARTICNO)

d) some further information regarding those who are over the threshold age for the site, indicating that they might have been a participant in the original baseline survey

e) any available information regarding those baseline participants who were registered to that address

Note that the LIFE2YEARS IDs (HOUSENO and PARTICNO) will differ from the original HOUSEID and PARTICID allocated in the baseline survey. However, for those older people who were participants in our earlier 10/66 surveys these two sets of IDs will be linked in one data file (partreg.rec – see below) permitting the new LIFE2YEARS data to be linked to our earlier databases.

3.2.3 How is this information to be recorded?

The results of the door-knocking process will be entered onto three types of data sheet, as below

| Data sheet | To be completed | Filename | Data entry file |
| --- | --- | --- | --- |
| Household register | One per household | HOUSEREG.pdf | HOUSEREG.rec |
| Participant register | One per current resident aged >=65 years | PARTREG.pdf | PARTREG.rec |
| Participant tracing | One per 10/66 baseline participant linked to that address on the register | DKTRACE.pdf | DKTRACE.rec |

The household register (HOUSEREG) contains the following information on ALL households doorknocked. By this we mean households with no older residents, as well as those with older residents. This will be used to estimate the composition of the total population and the response rate among older residents:

HOUSENO 	The household identifier, up to four digits

PERS15	Number of persons aged 15 or under

PERS1639	Number of persons aged 16-39

PERS4064	Number of persons aged 40-64

PERS65	Number of persons definitely, or possibly, aged 65 years or over

ADD1		Up to three lines for the address (open field variables)

ADD2

ADD3

NOTES	Another open field variable in which useful information for the

survey team could be entered, only  for houses with eligible older

participants e.g

‘no one in until after 6pm’, or

‘73yo man moving in October’ or

‘entrance through back of shop’

The participant register (PARTREG) contains the following information on each potentially eligible current resident (questions in italics will only be asked of those over the threshold age for the site, who may then have been participants in the original baseline 10/66 survey – see )

HOUSENO 	The household identifier, up to four digits (the same as entered

in the household register)

PARTICNO	Participant identifier. This is a unique identifier within each

household. That is, within each household, no two older eligible people will have the same identifier. However, eligible people in different households will have the same identifier. As we do not anticipate to find more than 9 eligible persons in a single household, this variable has a single digit. Allocate ‘1’ to the oldest eligible resident, ‘2’ to the next oldest, and so on.

NAME1	First name. Open field variable

NAME2	Second name. Open field variable

AGE	Age in years

AGEELIG	Is this person over the threshold age for your centre?

PART1066	Do they or anyone else in the household recall them taking part in a previous wave of the 1066 survey

HOMEMOVE	Have they moved since the baseline survey?

MOVEIN	Was that from another address within the catchment area (if yes, record address)

MOVEOUT	Was that an address outside of the catchment area (if yes, record date moved)

LINK	Has a confident link been made to baseline register ID

HOUSEID	Linkage to baseline survey HOUSEID (regardless of whether or not the individual is still resident at the same address)

PARTICID	Linkage to baseline survey PARTICID

The participant tracing data sheet (DKTRACE) will be completed for each 10/66 baseline survey participant previously linked to that address, using the form DKTRACE. This will include the following information

DKTRACE	The current status of that survey participant (dead/ moved away/ currently resident/ no information)

DKDOD	Date of death (for those reported to have died).

DKMADD	Participant’s new address (for those reported to have moved away)

DKTEL	Participant’s telephone number (for those reported to have moved away)

KIADD	Key informant address (for those reported to have died or moved away)

KITEL	Key informant telephone number (for those reported to have died or moved away)

3.2.4 Door-knock register data management

The household and participant databases are enormously important, particularly for ensuring accurate follow-up for LIFE2YEARS. Please send these files as soon as door-knock data entry is completed, to the data manager (Chong Kua). We will need to clean the data, check for completeness, and accuracy of data linkage before you commence interviewing in the field. The data are sensitive, since they include identifiable information (names and addresses). All register data will be stored, encrypted and password protected on the main KCL data server to protect against data loss. You should keep an electronic copy of your local register, securely, as well. Paper copies (data entry sheets) must be kept in a locked filing cabinet, separate from other survey data.

3.2.5. Situation at the end of the door-knock phase

You will have an accurate up to date register of all those aged 65 years and over currently residing in the catchment area. Therefore, once the door-knocking register is completed, you can commence the prevalence wave sample interviewing.

You will also have had the opportunity to

a) identify which current residents were participants in previous waves of the 10/66 survey, and linked their new IDs (HOUSENO and PARTICNO) to their original IDs (HOUSEID and PARTICID).

b) find out information about the status of other previous participants who may have died, or moved away out of the catchment area

3.2.6 Tracing and linkage, during the door-knocking process

This will occur in two ways

a) ‘top-down’ – when visiting an address identified on the register of baseline participants, the door-knocker will also check for the presence or current whereabouts (including vital status) of those previous residents who were participants in the baseline survey and are not yet known to have died

- If they are still resident, they should be registered in the LIFE2YEARS prevalence wave register, where a link made to the original HOUSEID and PARTICID (see above)

- If they have died, a note should be made of the data of death, and a possible key informant for the verbal autopsy interview

- If they have moved away, a note should be made of the new address (if known) and any other contact information (e.g. phone number)

b) ‘bottom-up’ – whenever a current resident of xx years or over (where xx is defined as 65 + the interval between the last baseline interview for that site and the date of door-knocking) is identified during the door-knocking they should be asked

i) were they resident in the catchment area in 200x (date of the baseline interview)?

ii) do they recall taking part in previous surveys?

A search will then be made in the database of participants surviving up to the incidence phase, for a match.

Whenever a confident match is made, the original HOUSEID and PARTICID will be linked to the new HOUSENO and PARTICNO.

At the end of the door-knocking, we will not necessarily have completed the linkage process, that is definitively identifying which of those in the new LIFE2YEARS register were participants in the original baseline survey, and linking them to a specific HOUSEID and PARTICID. Neither will we have traced all of the original baseline participants, particularly those that have moved to an address outside of the catchment area, or who had died (and hence would not be picked up by the door-knocking process). You should not take time, during the door-knocking process, to follow-up on the three contact addresses and phone numbers provided at baseline, or to check addresses outside of the catchment area. This would slow the process down. Once the LIFE2YEARS register is completed, we can start the prevalence wave sample interviewing. The remaining work of linkage and tracing can be completed in parallel with the prevalence wave sample interviewing.

3.3 Tracing and recontacting remaining baseline participants, not resident in the catchment area (final incidence wave)

Those that have moved away from the catchment area will not be part of the ‘new prevalence wave’.

This tracing work for the remaining participants for the final incidence wave is important, but should not be allowed to delay progress with interviewing new prevalence wave participants.

Final incidence wave participants who are not currently resident in the catchment area will retain their original 10/66 survey identifiers (HOUSEID and PARTICID) but will NOT be awarded LIFE2YEARS identifiers (HOUSENO and PARTICNO). Their data will not be entered onto the LIFE2YEARS survey register, so no HOUSEREG or PARTREG sheets need to be completed

Loss to follow-up is the biggest challenge to validity of findings from cohort studies. For the ‘final cohort’ we need to make every effort to get as much information as possible about every baseline participant, including those who have moved away. As well as those who were reinterviewed at follow-up, we also need to trace and interview those who refused, could not be traced, or were uncontactable at follow-up. They may now be traceable and/ or willing to be interviewed. As in the previous incidence wave, we aim to place every registered baseline participant who is not yet known to have died into one of five categories for status at LIFE2YEARS follow-up

1) Died

2) Refused

3) Reinterviewed

4) Not traced (not at previous address and no information about current status)

5) Uncontactable (apparently still at current address but cannot be contacted)

As will the last 10/66 incidence wave, we will enter these data into the STATUS.reg database

We will use broadly the same procedures to trace and recontact surviving baseline participants as was used in the incidence wave. The LIFE2YEARS tracing process is different in that we are systematically visiting all households in the catchment area for the purposes of the door-knocking, and the first attempt to trace surviving baseline participants (to the households where they were living at that time) will occur during that phase. During the door knocking you may find that an older person registered to that address

| Outcome | Action to be taken |
| --- | --- |
| 1. died | try to identify a key informant for the ‘verbal autopsy’ and ‘informant_deceased’ interviews |
| 2. still resident | they should be interviewed |
| 3. moved to another address within the catchment area | confirm this during the door-knocking, re-register participant to that new address, and interview |
| 4. moved to another address outside the catchment area | if feasible, trace them to that address, and interview |
| 5. no available information | follow procedures used for previous 10/66 incidence wave study |

Actions to be followed under 1-3 above have already been summarised in sections 3.1 to 3.2 above. This section focuses on procedures to be used where the participant is thought to have moved outside of the catchment area, or, if no information has been obtained about them during the door-kocking process.

If there is no information regarding the whereabouts of the baseline participant, you should follow the procedure used in incidence wave survey

- neighbours may be able to advise if the person still lives there, has died, is travelling, or has moved away.

- the names and contact details of three people who know the participant well and live close by were obtained in the baseline (HOUSEHOLD) interview. If necessary these people should be contacted in order to locate the participant

Where you have obtained a new address or contact for a participant who has moved out of the catchment area (either from the door-knocking or from contacting the three non-coresident informants) , you should again follow the procedure used in the incidence wave survey (summarised in the chart on the next page)

- those who have moved away should still be contacted and reinterviewed wherever possible. If the new address is too far away, then a telephone interview should be considered.

- if when following up the new address, you believe that the participant may be resident there, you should make at least 5 more repeat visits before declaring the participant to be ‘not contacted’. Some of these visits should be at different times of day (including evenings) and at weekends.

- For each participant, the door-knocker should complete the contact proforma for each attempt to trace the participant. This will log the process of tracing the participant, and the study coordinator will be able to review these sheets to ensure that the protocol on the flow chart has been followed, and that the outcome of this process has been correctly allocated.

DIED (informant interview and verbal autopsy)

RETURN TO BASE

Died

No match

REFUSED

No consent

Definitive match

INTERVIEW

Consent

Response to door knocking

contact

contacted

Information from neighbours/contacts

Participant still lives at address

Not contacted after 5 visits

Accessible

Name and

Address

NOT TRACED

(informant interview)

UNCONTACTABLE (informant interview)

Not

accessible

No response to door-knocking  and no information from neighbours/ contacts

No contact or information after 5 visits

Moved away

New address

identified

No new address

identified

3.4 The prevalence and incidence wave survey interviews

We should focus first on completing the interviews of those who are currently living in the catchment area (both previous 10/66 participants, and those newly eligible for LIFE2YEARS) – that is, the ‘new prevalence wave’ (see 1.5 ‘timelines’). Those previous participants who have moved out of the catchment area (part of the ‘final incidence wave’) can be traced by door-knockers as the catchment area interviews are progressing, and, where feasible, their interviews can be carried out towards the end of the data collection period. In contrast to the incidence wave, we will not stratify the order of interviews by dementia status, and those with and without previously noted dementia will receive the same interviews. With the new LIFE2YEARS participants (not previously interviewed), it would have been too complicated to follow this protocol.

3.4.1 The setting

This should be in the participant’s own home, unless the participant specifically requests to be assessed at a clinical centre.

3.4.2 Two interviewers or one?

Two interviewers working together may provide better security in ‘dangerous’ areas of town. One interviewer could interview the older participant while the other interviews the informant. This can be particularly useful for demented participants where the caregiver may not be able to leave them alone. Also it would minimise the amount of time spent in the household, thus minimising disruption to the family’s routine. This may or may not turn out to be the best method for your centre.

3.4.3 One session or more?

Ideally, we should aim to gather all the information in one session. However, if you find that the older participant is fatigued, you could go back to complete the interview on another occasion. Also, you may need to return on another occasion to interview the informant when they are back from work. Remember however, that the family is more likely to consent to the first approach. If you say you have to go back to them, they may refuse. In the baseline this was a particular problem when the physical examination was carried out in a separate session.

3.5 Blood sample collection

We aim to collect fasting blood samples from all prevalence and incidence wave participants. Blood samples should be collected as soon as possible after the survey interview. Participants may consent to the survey while still declining to give a blood sample. However, blood samples will not be taken unless the survey has been completed, to the extent possible. (See 7. PLANNING FOR BLOOD SAMPLE COLLECTION for further details of blood sample collection, processing, storage, and transport).

3.6 18 month nested cohort study

In order to test the predictive validity of frailty indicators, a sub-sample of participants in the main LIFE2YEARS survey will be selected for participation in a further nested cohort study. Inclusion criteria will be

- Took part in the prevalence wave LIFE2YEARS survey (i.e. those that were in the incidence wave survey only will be excluded)

- Donated a blood sample, which has been received in London

- Did not have any needs for care

From among those meeting inclusion criteria, age, gender, frailty, chronic diseases and NEUROEX findings will be used to identify 150 participants who might be expected to have a high risk of incident dependence and 150 participants with lower risk, 300 in total, from each country. Intensive biomarker testing will then be carried out on the samples collected from these participants. Participants will be re-contacted to request their consent for participation in follow-up data collection 18 months after their LIFE2YEARS baseline interview.  Data to be collected at follow-up will comprise: vital status, needs for care, WHODAS 2.0 disability, cognitive function, and any significant health and life events in the intervening period.

The London centre will run the algorithms to select the participants. If interviewing proceeds at a relatively fast pace, as planned (aiming to complete at least the catchment area interviews in one year), we will have the luxury of making the final selection of cohort participants when the interviewing is complete, meaning that we can carry out a truly random selection of ‘high risk’ and ‘low risk’ cohort participants, allowing ‘weighting back’ of findings from the nested cohort to the population as a whole, and analyses on the whole sample, imputing missing outcomes.

4. THE ASSESSMENTS

4.1 Overall structure

The assessments to be administered in the course of 10/66 LIFE2YEARS are best understood as, in effect, comprising three sets, used for different purposes and under different circumstances

- Set A should be administered to all participants in the prevalence wave survey, and all surviving participants for the final incidence wave

- Set B should be administered to an informant for those in the final incidence wave who are found to be deceased,

- Set C will be administered as a follow-up to the 300 participants who, having received set A, were selected for the nested cohort

- Hence, either Set A or Set B will be used, not both. However, all those that receive Set C will have been interviewed with Set A 18 months previously.

Study coordinators, interviewers and data managers will need to be familiar with this assessment structure, and with the questionnaires, data coding sheets and data entry files that are provided for each assessment.

For every visit in the main LIFE2YEARS survey, interviewers will need to carry with them one copy of each of the seven assessments in SET A and the two assessments in SET B, and multiple copies of the corresponding data coding sheets. They will also have ‘contact sheets’ for each set of assessments. They will use these to indicate, for each potential participant, their interview status (dead/ refused/ interviewed/ uncontactable/ ineligible) and for those that were interviewed, which of the assessments in the relevant set have been completed.

Interviewers will need to be trained, in the first instance, in the administration of Set A and B. Since not all of the interviewers will need to be retained for the nested cohort follow-up, the minimal training required in the administration of Set C questionnaires should be carried out immediately before the beginning of the follow-up period

4.2 Overview of the structure of the LIFE2YEARS assessments – Set A

Set A of the LIFE2YEARS assessments comprise the basic survey assessments for the new prevalence wave and final incidence wave participants. These include those that are administered to the head of household, those administered to the older person, and those administered to an informant who knows the older person well

4.2.1 Household assessments

At the outset of the interview, with the household members gathered together, the interviewer collects information about the household as a whole. The interview has been substantially modified from previous waves of the 10/66 survey, and this information now only needs to be collected once for each household, even if there are several eligible participants

Household interview (HOUSEHOLD)

In the Household interview, the interviewer ascertains names of contacts to facilitate tracing household participants at a later date, the household composition (who lives there), and some indicators of household economic status. This interview is administered to the head of household, but others may contribute information.

Data is entered into HOUSE.rec

4.2.2 Assessments for the older participant

The following assessments are all administered to the older person. The cognitive interview and the Geriatric Mental State should be administered, if possible, to the older person in private. The NEUROEX can be administered in private, or with a family member present, according to the preferences of the older person.

Cognitive interview (COGNITIVE)

The cognitive interview comprises the cognitive component of the CSI ‘D’ (COGSCORE), and the CERAD animal naming and 10 word list-learning tests. The version used in LIFE2YEARS is identical to that used in the all previous 10/66 surveys

Data is entered into COG.rec

Geriatric Mental State (GMS)

As in previous waves of the 10/66 survey, we use the B3 (community) version of the GMS, which generates information, through its AGECAT algorithm on the presence of clinically significant and subsyndromal features of depression, anxiety, psychosis and ‘organicity’ (dementia or delirium). The version used in LIFE2YEARS is identical to that used in the last 10/66 incidence wave survey

Data is entered into GMS.rec

Background socio-demographic and risk factor questionnaire - participant version (BACKGROUND PARTICIPANT).

This assessment covers sociodemographic information, life history, medical history, lifestyle and behavioural risk factors, current health status, and health service utilization. The LIFE2YEARS version is a synthesis of the previous 10/66 baseline and incidence wave versions, with some redundant sections omitted

Data is entered into BACK_PART.rec

NEUROEX – Physical assessment and brief neurological examination (NEUROEX)

This assessment comprises elements from the baseline and incidence wave questionnaires; pulse and blood pressure; anthropometric measures; dentition assessment; a brief structured neurological assessment; and an interviewer rating of mobility. To strengthen assessment of frailty phenotype we have added spirometry and hand grip strength, and elements from the WHO-COPE assessment tool (chair stand test, visual acuity, whispered voice hearing test).

Data is entered into NEUROEX.rec

4.2.3 Assessments for the informant

These assessments are administered to an informant (usually but not necessarily a co-resident and/ or family member). The main qualification is that they should know the older person’s current and/ or recent circumstances well. See section x.x## for further guidance on selection of a suitable informant. When the participant is alive, the informant interview is administered for all participants, and the proxy version of the background interview is administered when there is any doubt about the validity of the participant’s responses to the background sociodemographic and risk factor questionnaire.

Informant interview (INFORMANT)

The informant interview solicits information regarding; background information about the informant; needs for care; care arrangements and caregiver strain (where there are needs for care); the informant section of the CSI’D’ (RELSCORE) asking about cognitive and functional decline; the ‘History and Aetiology Schedule – Dementia Diagnosis and Subtype’ (HAS-DDS) giving information on onset and course of dementia (administered only when CSI’D’ identifies some cognitive and functional decline) and the NPI-Q (Behavioural and Psychological Symptoms of Dementia), administered to all informants. The LIFE2YEARS version is similar to that used in the last 10/66 incidence wave survey, but briefer, since large sections of the HAS-DDS (which were not relevant to dementia subtype allocation) have been omitted

Data is entered into INF.rec

Background socio-demographic and risk factor questionnaire - proxy version BACKGROUND PROXY)

The content of this interview is essentially identical to that of the participant version (see 4.2.2 above), and is administered instead of, or in addition to the participant version where the participant has too severe dementia or is otherwise unable to answer the questions reliably.

Data is entered into BACK_PROX.rec

4.3 Overview of the structure of the LIFE2YEARS assessments – Set B

Where a participant in the final incidence wave is traced and found to be dead, Set B assessments are used rather than Set A. Set B assessments are administered to a suitable informant only.

The objective is to gather information on date and cause of death, and possible onset of dementia before death, for the purposes of completing the study of incident  dementia and mortality from the original 10/66 baseline cohort. Therefore, this information should only be collected on those in the original baseline whose deaths have not previously been documented (hence eligible for the final incidence wave), and who have died before a LIFE2YEARS survey assessment could be carried out. These interviews should NOT be administered for new prevalence wave participants who were not in the original baseline survey, even if they die during the course of the project.

Verbal autopsy

The verbal autopsy informant interview is a fully structured interview covering symptoms and signs that the older person may have exhibited in the period leading up to death, and the date and circumstances of death. It is used to establish date of death and probable cause or causes of death. This assessment is identical to that used in the last 10/66 incidence wave survey.

Data is entered into VA.rec

Informant (deceased) questionnaire

The Informant (deceased) interview is a greatly reduced version of the full informant interview, and is much briefer than the informant (deceased) questionnaire used in the last 10/66 incidence wave.  The purpose is to determine if the participant might have developed dementia between their last interview and the date of death. Therefore this only needs to be administered to those who have not previously had an onset of dementia documented in earlier 10/66 surveys (this information will be provided on the cohort register). The interview only includes the CSI-D informant section, the time of onset of relevant symptoms, and any help-seeking for cognitive and functional problems.

4.4 Overview of the structure of the LIFE2YEARS assessments – Set C

Older person interview (participant version)

This interview comprises

a) a considerably abbreviated version of the baseline background participant interview, focusing on health and functioning only.

b) some new questions on significant life events that may have occurred in the interval since the baseline interview for the cohort. These are taken from the ‘List of threatening events’ (Brugha et al 1985).

c) the cognitive interview, as per 4.2.2. above

The cognitive interview must be administered to all nested cohort participants. However, there is a proxy version of a) and b) above, which can be administered to an informant, in addition to, or instead of the participant version when the quality of the data provided by the participant is in doubt

Older person interview (proxy version)

See above

Short informant interview

This is a considerably abbreviated version of the main LIFE2YEARS survey informant questionnaire, focusing only on the care module (identifying needs for care), the informant CSI-D (changes in cognitive and functional status) and the NPI-Q (neuropsychiatric symptoms)

Short physical and neurological exam

This is a somewhat abbreviated version of the main LIFE2YEARS survey NEUROEX. All anthopometric assessments (which are unlikely to have changed), excepting weight, are excluded. Everything else remains the same.

This information is summarised schematically in Table 4.1 (below), with the full title of each assessment, the short title, and the brief code to link to each assessment. We anticipate that the short title will be used in routine communication between project staff and investigators. The code will be used to identify the files (full questionnaires, data coding sheets and data entry files) for each assessment.

Table 4.1

| SET | Application | Full title | Short title | CODE |
| --- | --- | --- | --- | --- |
| A | Main survey assessments, to be administered for each participant in the new prevalence wave survey and/ or the final incidence wave | Household questionnaire | HOUSEHOLD | HOUSE |
|  |  | Cognitive interview | COGNITIVE | COG |
|  |  | Geriatric Mental State | GMS | GMS |
|  |  | Background socio-demographic and risk factor questionnaire (participant version) | BACKGROUND PARTICIPANT | BACK_PART |
|  |  | Background socio-demographic and risk factor questionnaire (proxy version) | BACKGROUND PROXY | BACK_PROX |
|  |  | Physical assessment and neurological examination | NEUROEX | NEUROEX |
|  |  | Informant interview | INFORMANT | INF |
| B | Main survey assessments to be administered when a participant in the final incidence wave is found to be deceased | Informant interview | INFORMANT (DECEASED) | INF_DEC |
|  |  | Verbal autopsy | VA | VA |
| C | 18 month follow-up assessment for the 300 participants selected for the nested cohort study | Older person interview (participant version) | OLDER PERSON PARTICIPANT FU | FU_OP_PART |
|  |  | Older person interview (proxy version) | OLDER PERSON PROXY FU | FU_OP_PROX |
|  |  | Short informant interview | INFORMANT FU | FU_INF |
|  |  | Short physical and neurological exam | NEUROEX FU | FU_NEUROEX |

4.5 Translation of assessments

There are very few new questions to be translated, and these are mostly instructions to the interviewer for the new examinations in the NEUROEX. These will be forward translated, and reviewed by the PIs and other clinicians in each site, and assessed for comprehensibility in a brief pilot (see section 9)

The question regarding a previous diagnosis of dementia or Alzheimer’s disease would merit being presented to a panel including

a) Local older people similar to those who will take part in the study

b) Alzheimer Association volunteers

c) Local experts, clinician specialists, health care workers etc.

The aim of this exercise is to test the conceptual validity of the translated version. Do the experts and the older people understand the items in the way that is intended? If not, explain the intended meaning to the panel and see if they can come up with a better translation. Update the translated version accordingly to arrive at a final version.

4.6 Further information on assessments

Further and more detailed information regarding each assessment and its administration can be found in the interviewer manual NOTES ON SPECIFIC ASSESSMENTS

Each assessment is linked to a full questionnaire (pdf), a data coding sheet (pdf) and a data entry file (rec). These will be provided by the London Centre. File names are listed in Appendix 1

Further information on the specific changes that have been made to earlier versions of 10/66 questionnaires can be found in Appendix 2

5. FEEDBACK TO PARTICIPANTS

We are all agreed that we need to work towards improving the speed, responsiveness and scope of feedback provided to survey participants. Note that while we will offer this service, participants have the right to decline to receive feedback, if they do not wish to receive this information

1. Local community health care services, and any other relevant services and stakeholders need to be informed of the project, with arrangements for referral and/ or help-seeking discussed in advance

2. Simple structured feedback may be provided directly by interviewers at the end of the assessment (for example, blood pressure level). Interviewers also need to be provided with a list of red flags, which they should discuss urgently with SC and/ or PI. (The protocol for this needs to be developed, and interviewers trained appropriately)

3. Depending upon frequency of transport of specimens to the UK, it may take a period of a few months to feedback detailed blood test results. However, point of care blood glucose assessments could be fed back immediately, and FBC results could be fed back immediately by local laboratories (via the field research team)

4. More comprehensive feedback on a participants overall health profile, and possible unmet healthcare needs could be generated automatically from data sent to the London centre, with a printed summary generated automatically for each participant (the mechanism for this needs to be developed by the London team and the text template discussed with each Centre). Individualised feedback should be provided by the local team who should be prepared to answer questions, and provide advice and support where necessary (i.e. the printed summary should not simply be posted through the door)

6. RESEARCH WORKER TRAINING

The PI and the SC will jointly be responsible for training the doorknockers and interviewers. Specific suggestions for the structure, content and methods for the training, have been provided, with a comprehensive manual for the trainees.

6.1 Training of doorknockers

Door-knocking team members need to

a) understand enough about the study aims, objectives, and protocol to answer, at a basic level, questions that residents might have about the project

b) adopt a professional and polite manner in approaching members of the public and requesting information

c) be able to follow, accurately, a structured algorithmic approach in seeking and recording information on a door-knocking proforma

d) understand the need to be diligent in performing these tasks

A one day structured training program should suffice. However, after training, they should be supervised closely in the field, and spot checks should be carried out to ensure comprehensiveness and accuracy.

6.2 Training for interviewers,

For new interviewers, as with the baseline study a minimum period of five training days is required. For those interviewers who worked on the original baseline and/ or incidence surveys, a two day refresher will be sufficient.

For the population-based research, the key elements of the training would comprise

1) Overview of incidence phase study aims and methodology

2) Training and practice in the correct approach to obtaining informed consent, with particular reference to the nature of informed consent (including the need to avoid any element of coercion), assessing capacity (and what to do if there are doubts regarding the capacity of potential participants to give informed consent)

3) Detailed training in the clinical assessments

a) GMS

b) NEUROEX

English language videos have been made available for training for GMS and NEUROEX. These may be dubbed in your local language, or you may wish to prepare local language versions. Spanish GMS training videos (Daisy Acosta) are already available.

4) General training in the fully structured assessments

a) CSI ‘D’

b) Informant/ caregiver interview, including the HAS-DDS and NPI

c) Background and Risk factor interview

d) Verbal autopsy (for informants of the deceased)

This should comprise general training in the principles of structured interviewing (asking questions and coding responses), familiarity in the scope and content of the questionnaires, and practice with administration and rating.

5) Training in data handling and quality control procedures (see also below)

7. PLANNING FOR BLOOD SAMPLE COLLECTION

As for the baseline blood sample collection, we plan to collect 10 hour fasting blood samples on all prevalence wave participants. These will therefore need to be collected, by an accredited phlebotomist, in participants’ homes, early in the morning. Appointments will need to be made in advance, and clear fasting instructions will need to be given. A breakfast snack could be provided as a gift after the sample has been taken.

The participant should be seated (not lying down) when the sample is taken. Samples will be taken via a butterfly cannula into vacutainer tubes.

It is essential that the sample bottles are labelled properly, with the HOUSENO and PARTICNO, and gender of the participant. No other personal identifiers, particularly names or addresses should be written on the label

Haematology/ FBC analyses will need to be carried out at a local laboratory.

The 10ml clot and 2.5ml Fluoride oxalate bottles will need to be centrifuged locally and frozen at -20C.

Samples will then be transported in batches to the UK for DNA extraction, genotyping, and serum chemistry assays

The procedures for sample collection, processing, storage and assay are summarised according to the schema outlined in Table 7.1 below

Table 7.1 Blood sample collection and processing

| Blood collection | 15-20 ml venous blood |  |  |
| --- | --- | --- | --- |
| Initial storage | 5-10 ml plastic EDTA | 2.5ml fluoride oxalate | 10ml plain clot |
| Initial processing at lab | Analyse FBC haemoglobin, MCV and MCHC | Centrifuge fluoride oxalate | Centrifuge 10ml clot |
| Samples for freezing (temp for freezing) | keep and freeze remaining EDTA in original plastic EDTA tube (-70C, or if not possible at -20C) | Freeze serum at -20C | Freeze serum at -20C |
| Analyses to be conducted in UK by King’s College Hospital Clinical Biochemistry, and fast throughput genotyping service | DNA extraction, genotyping and storage | King’s College Hospital Clinical Biochemistry Cytokines (ELISA) Glucose, lipids, albumin, testosterone, SHBG (Advia multichannel analyser system) Telomere length (Southern blot , possibly HT Q-FISH, depending on costs) |  |

The main issues to be considered regarding the logistics of this process (which may vary from site to site) are

1. How can we incentivise participants to provide a sample? This may be particularly difficult in China where there is a cultural reluctance to donate blood, and older people may already have had routine blood tests performed by local public health services. We can and should offer to feedback blood test results. This can be done immediately for fasting glucose if we also carry out a point of care test onsite. The FBC results could be relayed rapidly from the local laboratory. However, the other test results, from samples sent to the UK, may take up to 2 months to be returned, depending upon the frequency with which samples are transported to the UK. If there is a low response rate in China, we may need to consider offering saliva collections (for DNA only) for those who refuse phlebotomy.

2. Each centre needs to identify a local laboratory which could carry out centrifuging of samples and FBC analysis. Unfortunately we would not be able to offer them a fee for service due to EU funding rules. We could, however, offer to purchase for them a stock of laboratory equipment (pipettes, reagents etc) used for these tests.

3. It may be difficult in some sites (particularly rural Mexico and Peru) to get samples to a centrifuge quickly enough to meet the requirements for the glucose and other serum chemistry analyses. We may need to consider purchasing portable centrifuges, and asking the phlebotomist to carry out these tasks, in the field, instead.

4. we need to negotiate approvals for transport of samples to the UK, supported by standard Material Transport Agreements.

8. ETHICAL ASPECTS

8.1 Ethics review

To proceed with these studies, we need ethical approval both from the UK Institute of Psychiatry ethical review board, and the ethical review board at your local institution. We have prepared ethical submissions for the incidence phase, and obtained permission from the UK King’s College Research Ethics Committee for the studies in Cuba, Mexico, Peru, Venezuela, Dominican Republic, Puerto Rico and China. We have forwarded to you copies of the ethical submissions, together with the study information sheets and consent forms.

Please use these submissions, and the information sheets and consent forms as the basis for the submission to your to local ethical review boards. It is essential that you inform us of any changes that your local ethical review board would like to see made to these procedures, so that we can inform our board of them. Please translate the information sheets and consent forms into your local languages for use in your centres.

Essential elements of the general consent include

1) the participant is free to decide not to take part

2) there will be no negative consequences of a decision no to take part, particularly for their clinical care

3) if they do decide to take part, they can drop out at any time, without giving reasons

4) the name and contact details of the investigator must be listed on the consent form and the information sheet. A copy of both must be left with the participant, and a copy of each must be retained by the local investigators.

5) in the event that the participant does not have the capacity to give informed consent (eg dementia), then the information sheet should be read to them in the presence of a family member, who confirms that this has been done, that there was no sign of dissent from the person with dementia, and that they, the family member agree to the participation of the person with dementia

6) in the event that the participant cannot read or write, they should not be asked to sign the consent form, but the investigator signs that they have assented, and this is witnessed (if possible) by an independent person who can read and write.

Essential elements of informed consent for DNA collection include informing the participant

1) they are making a gift of the DNA to a custodian (the local research centre). Note that ownership is retained by the participant

2) the general areas of research that will be addressed by the genotyping that will be carried out

3) that they will not have any claim to any intellectual property (IP), including financial exploitation, arising out of their gift of DNA

8.2 Training interviewers in approaching potential participants, and seeking and obtaining informed consent

All interviewers will need to be trained, monitored and supervised in correct procedures for obtaining informed consent. This must include:

a) understanding what is informed and autonomous consent

b) understand and be able to communicate clearly and simply the objectives of the project, and the main risks and benefits that are involved.

c) be familiar with the various information sheets and consent forms, and the circumstances in which they should be used

d) be competent to assess capacity to consent.

Comprehensive guidance is provided in the interviewer manual

In the training process, interviewers should practice obtaining informed consent with the trainer role playing the participant, informant or head of household. They should then be supervised in your first few attempts to obtain informed consent in the field, and monitored from time to time thereafter. All consent forms should be reviewed by the study coordinator to ensure

a) that we have a valid set of consent forms for every participant, on file and that

b) these have been correctly completed

9. PILOT STUDIES

###### Following discussion in Madrid, we agreed that full piloting of the entire LIFE2YEARS interview would not be necessary, since the scope, content and duration of the interviews remained very similar to that used in the previous baseline and incidence waves, and since there are very few entirely new elements. However,

###### a) the NEUROEX is now longer, and includes several physical performance measures. This should be piloted on 5-10 older volunteers in each country (not participants in the research), who should include frail as well as non-frail individuals. The length of the overall NEUROEX assessment should be noted, and recorded, and the respondent and interviews impressions recorded, particularly with respect to the feasibility and tolerability of the new elements and the overall assessment

###### b) the blood sample collection, local transport and local processing protocols should be assessed and fine tuned to ensure optimally efficient collection and transport to laboratories.

10. READY TO GO!

Having completed stages 1. to 9. you should now be ready to implement the full study protocol in your centre.

11. IMPLEMENTATION OF THE SURVEY PROTOCOL

The more detailed aspects of the implementation of the survey protocol are covered in the separate manuals that have been prepared for the key project personnel, namely

- Study coordinator

- Data manager

- Interviewers

- Door-knockers

- Phlebotomist

These manuals are intended to be guides that the staff should refer to throughout their work on the project

They should also be used for the purposes of training, supervision and quality control

APPENDIX 1

Data collection and data entry resources

As described in the main study manual, the LIFE2YEARS survey will use three sets of questionnaires

Set A comprising the main household, older person and informant assessments for the LIFE2YEARS new prevalence wave and final incidence wave survey

Set B comprising the informant interviews to be carried out when a potential participant in the final incidence wave survey is found to be deceased

Set Comprising the interviews to be carried out at 18 month follow-up of the 300 participants selected for the nested cohort study

Each questionnaire is linked to a data coding sheet, and an EpiDATA data entry file. For each set of assessments, there is also a ‘contact sheet’ on which the interviewer records, for each participant potentially eligible for that block of assessments, the outcome of the contact and consent process, and which assessments in the set have been completed.

It is the responsibility of the data manager to ensure that they have received copies of each of these files, and that everything is in order. Further copies can be obtained from London, or downloaded from the 10/66 website

It is the responsibility of the study coordinator to ensure that every interviewer goes into the field with hard copies of all of the assessments in Sets A and B (for the main LIFE2YEARS survey) and has adequate copies of the data coding sheets. Participant responses can be recorded by hand using coding sheets, instead of the actual questionnaires (to reduce printing costs).

The assessments in Set A, Set B and Set C, and the names of the questionnaire files, the data coding sheet files and the data entry files are tabulated on the following pages

Table 1 – Set A documents

| Set A Documents | Questionnaire file name | Data coding sheet file name | Data entry file name |
| --- | --- | --- | --- |
| Household interview | HOUSE.pdf | Code HOUSE.pdf | HOUSE.rec |
| Cognitive assessment | COG.pdf | Code COG.pdf | COG.rec |
| Geriatric Mental State | GMS.pdf | Code GMS.pdf | GMS.rec |
| Sociodemographic and risk factor (participant version) | BACK_PART.pdf | Code BACK_PART.pdf | BACK_PART.rec |
| Sociodemographic and risk factor (proxy versions) | BACK_PROX.pdf | Code BACK_PROX.pdf | BACK_PROX.rec |
| Physical and neurological exam | NEURO.pdf | Code NEURO.pdf | NEURO.rec |
| Informant interview | INF.pdf | Code INF.pdf | INF.rec |
| Contact sheet |  | Code A_CONTACT.pdf | A_CONTACT.rec |

Table 2 – Set B documents

| Set B Documents | Questionnaire file name | Data coding sheet file name | Data entry file name |
| --- | --- | --- | --- |
| Informant interview (deceased) | INF_DEC.pdf | Code INF_DEC.pdf | INF_DEC.rec |
| Verbal autopsy | VA.pdf | Code VA.pdf | VA.rec |
| Contact sheet |  | Code B_CONTACT.pdf | B_CONTACT.rec |

Table 3 – Set C documents

| Set C Documents | Questionnaire file name | Data coding sheet file name | Data entry file name |
| --- | --- | --- | --- |
| Older person interview (participant version) | FU_OP_PART.pdf | Code FU_OP_PART.pdf | FU_OP_PART.rec |
| Older person interview (proxy version) | FU_OP_PROX.pdf | Code FU_OP_PROX.pdf | FU_OP_PROX.rec |
| Short informant interview | FU_INF.pdf | Code FU_INF.pdf | FU_INF.rec |
| Short physical and neurological exam | FU_NEUROEX.pdf | Code FU_NEUROEX.pdf | FU_NEUROEX.rec |
| Contact sheet |  | Code C_CONTACT.pdf | C_CONTACT.rec |

APPENDIX 2

Overview of changes to questionnaires from previous waves

The questionnaires for the LIFE2YEARS phase of the population-based studies have now been sent to all centres. These are very similar to those used at baseline or follow-up, with

a) some additions from the INDEP study

b) a few completely new questions (which will need to be translated) and

c) deletions of redundant questions (not previously used in analyses).

Changes are highlighted in the table below:

| MODULE (STARTING POINT) | DELETIONS |  | ADDITIONS/ MODIFICATIONS |  |  |
| --- | --- | --- | --- | --- | --- |
| HOUSEHOLD | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| Household (Baseline) NOTE: The household questionnaire is now to be administered once only, for the whole household | Age ascertainment | 2. | Household composition grid | INDEP | 2. |
|  | Household composition questions | 3.3-3.6 | Additional household asset items | INDEP | 3.8.7-3.8.12 |
|  |  |  | Economic strain indicators | INDEP | 3.9 |
|  |  |  | Food consumption | INDEP | 3.10 and 3.11 |
| BACKGROUND_PARTICIPANT | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| Background_participant (Baseline) NOTES: 1. The baseline questionnaire is the starting point, since items that would not have changed were omitted for the FU 2. However, enhancements introduced at FU are retained 3. COPD is now diagnosed directly from spirometry 4. Other omitted items have rarely, if ever been used in previous analyses | Head of household questions | 4.1-4.2 | Age ascertainment | Moved from 10/66 HOUSEHOLD | 2. |
|  | COPD screen | 7.17-7.18 | Autonomy | INDEP | 6.13-6.16 |
|  | Infectious diseases | 7.19-7.21 | Met/unmet need | INDEP | 6.17-6.21 |
|  | Family history of dementia | 7.26-7.26.6 | When diagnosed with diabetes | NEW | 7.15.1 |
|  | Reproductive health | 11-11.4 | Hyperlipidaemia and statin prescription | 10/66 FU | 7.17 |
|  |  |  | Falls | 10/66 FU | 7.18 |
|  |  |  | Incontinence | 10/66 FU | 7.19 |
|  |  |  | Parkinson’s disease diagnosis | Moved from HAS-DDS | 7.20 |
|  |  |  | Dementia diagnosis | NEW | 7.21 |
|  |  |  | Oily fish | 10/66 FU | 12.3.3 +12.3.4 |
|  |  |  | Fruit and veg separated | 10/66 FU | 12.3.5 + 12.3.6 |
|  |  |  | Modified instructions for traditional healer question | NEW | 13.6.1 |
| INFORMANT | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| Informant (FU) NOTES: 1. Starting point is FU questionnaire (for those without dementia). This is the same as the baseline questionnaire, other than the help-seeking questions after the informant CSI-D. 2. HAS-DDS has been greatly abbreviated, retaining only those items that are used to generate DSM-IV dementia, and dementia sub-type diagnoses | Same informant as at baseline? | B1.0 | NO ADDITIONS |  |  |
|  | All of HAS-DDS other than | Retained TIMEONS TYPEONS ONS1 ONS11 ONS13 ONS14 ONS16 ONS22 FLUCT FLUCTCOG GRADDEC STEPWISE CLOUDING CONFNITE CONFDAY NOCTURN BCHANGE BIRRIT BUPSET BFIRST HI HILL LOC BECHANG EARLYCHG |  |  |  |
| COGNITIVE | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| Cognitive (Baseline) | Unnecessary translation notes | 16 |  |  |  |
| GMS | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| GMS (FU) NOTE: GMS FU is the same as baseline, other than the addition of help-seeking questions after subjective memory impairment | NO DELETIONS |  | NO ADDITIONS |  |  |
| NEUROEX | DELETIONS | QUESTION # | ADDITIONS/ MODIFICATIONS | SOURCE | QUESTION # |
| NEUROEX (Baseline) NOTES: 1. baseline is the starting point, abandoning the NIH stroke scale introduced at FU, and retaining the original structured neurological examination 2. Enhancements introduced at FU (weight, teeth and calf circumference) are retained. 3. Additional items (hand grip strength, chair stand test, spirometry, visual acuity and hearing) are core to assessment of frailty in LIFE2YEARS | Visual field defect | 8 | Changes to list of required equipment |  | PREAMBLE |
|  |  |  | Calf circumference | 10/66 FU | 2.5 |
|  |  |  | Hand grip strength | NEW | 17 |
|  |  |  | Spirometry | NEW | 18 |
|  |  |  | Weight | 10/66 FU | 19 |
|  |  |  | Dentures | 10/66 FU | 20 |
|  |  |  | Teeth count | 10/66 FU | 21 |
|  |  |  | Chair stand test | NEW – COPE | 22 |
|  |  |  | Mobility rating | 10/66 FU | 23 |
|  |  |  | Snellen Visual Acuity | NEW – COPE | 24 |
|  |  |  | Hearing – whisper voice test | NEW – COPE | 25 |